## Project Plan
|  | PROJECT NAME | PROJECT DURATION | PROJECT START DATE | PROJECT END DATE
|  | FANS-SPACE | 27 | 2022-03-28 | 2022-04-24
PROJECT PLAN | [12 empty] | GANTT CHART
Activity Number | Project Descomposition | Task Description | Estimated Hours | Actual Hours | Days | % Completed | Dependencies (Activity Number) | Start Date | End Date | Role | Person in Charge | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24
1 | Requirements | Identify the requirements needed and completed document | 3 | 6 | 2 | 100% | 0 | 2022-03-28 | 2022-03-30 | Analyst | Alwayne | bar: 2022-03-28 to 2022-03-30
2 | Flow Diagram | Define the flow and structure of project | 2 | 2 | 1 | 100% | 1 | 2022-03-31 | 2022-04-01 | Business Architect | Alwayne | bar: 2022-03-31 to 2022-04-01
3 | Architecture of Smart contracts | Define the architecture of the smart contracts and components | 3 | 5 | 1 | 100% | 2 | 2022-04-02 | 2022-04-03 | Blockchain Architect | Alwayne | bar: 2022-04-02 to 2022-04-03
4 | Data Definition | Define the data required by the smart contracts | 3 | 3 | 1 | 100% | 2.0, 3.0 | 2022-04-04 | 2022-04-05 | Data Architect | Alwayne | bar: 2022-04-04 to 2022-04-05
5 | Architecture of the web application | Define the architecture of the Web Application | 2 | 3 | 1 | 100% | 3.0, 4.0 | 2022-04-06 | 2022-04-07 | Application Architect | Alwayne | bar: 2022-04-06 to 2022-04-07
6 | Technology | Identify all the required Technologies needed for development, testing and deployment of the different components. | 2 | 1 | 1 | 100% | 2.0 ,3.0, 5.0 | 2022-04-08 | 2022-04-09 | Application Architect | Alwayne | bar: 2022-04-08 to 2022-04-09
| Fan-Token(Smart Contracts) | Development and test of smart contracts | 10 | 15
7 | Development |  | 7 | 12 | 3 | 100% | 3 | 2022-04-10 | 2022-04-13 | Blockchain Developer | Alwayne | bar: 2022-04-10 to 2022-04-13
8 | Test |  | 3 | 5 | 2 | 100% | 7 | 2022-04-14 | 2022-04-16 | Blockchain Developer | Alwayne | bar: 2022-04-14 to 2022-04-16
| Web User interface |  | 8 | 15
11 | Express |  | 4 | 7 | 1 | 100% | 8 | 2022-04-17 | 2022-04-18 | Developer | Alwayne | bar: 2022-04-17 to 2022-04-18
12 | React |  | 4 | 8 | 1 | 100% | 11 | 2022-04-19 | 2022-04-20 | Developer | Alwayne | bar: 2022-04-19 to 2022-04-20
| Integration | Development and test of the integration between the Web Application and Smart Contracts | 6 | 12 |  | 100%
13 | Develop Smart contract with Web Application |  | 6 | 12 | 3 | 100% | 12 | 2022-04-21 | 2022-04-24 | Blockchain Developer | Alwayne | bar: 2022-04-21 to 2022-04-24
|  | Total Hours | 63 | 106